## Slide 1
OCTOBER 28TH, 2026
San Matías Pipeline
Technical Committee Meeting N°5
Notes: REVISIÓN v02 — 27/10/2026. Se vuelve a la PPT original conservando sus gráficos y series. La v02 sustituye al borrador temático v01 como base vigente. El usuario confirma datos iguales y nuevas láminas de fotos/temas relevantes. Novedades pendientes de Leandro Doglio; no se recibieron fotografías reales. Fecha del comité conservada del original: 28/10/2026. No se ha emitido el informe.
ENTREGA VIGENTE v05: basada en el archivo que el usuario volvió a adjuntar. Orden: seguridad gráficos, seguridad novedades, ambiente gráficos, ambiente novedades. Se conserva el 2.87% y todos los datos de gráficos. La lámina ambiental se completa sin recuadros de fotos. Esta entrega sigue siendo borrador: faltan novedades de seguridad, fotos de esa sección y actualización del helicóptero.
CAMBIO VIGENTE v07: a pedido del usuario se retiran de esta PPT general los dos temas de permisos ambientales citados en su último mensaje. Se elimina la lámina narrativa que los contenía; se conservan los gráficos ambientales y todos sus valores. La presentación general queda en 8 láminas. Este cambio no modifica el estado real de los trámites ni implica aprobación o cierre de los temas omitidos.
CAMBIO VIGENTE v08: el usuario también solicita omitir la lámina de indicadores ambientales de residuos y agua. Se elimina la antigua posición 6, además de la lámina narrativa ambiental retirada en v07. La entrega general actual tiene 7 láminas; conserva seguridad, capacitación 2.87%, novedades de seguridad pendientes y helicóptero.

## Slide 2
AGENDA
1 > DEDICATED GAS PIPELINE UPDATE
2 > PERMITS
  1.1 > HSE Indicators
  1.2 > Schedule
  1.3 > Project’s Key Milestones
  1.4 > Project Progress
Agenda
CONFIDENTIAL
3 > HELICOPTER SERVICE (Update)
WORKING DRAFT · 27 OCT 2026
2

## Slide 3
1.1 > DEDICATED GAS PIPELINE UPDATE > HSE Indicators
CONFIDENTIAL
Statistics through 30 Sep 2026 · CP + Pipeline · October highlights reported separately
TRICF Frequency
0
Cum. Aug–Sep · target 2.35 Through 30 Sep 2026
TVCR Frequency
0
Cum. Aug–Sep · target 0.79 Through 30 Sep 2026
Cumulative to 30 Sep 2026
October KPIs · figures not provided
KPI | CP + Pipeline
DAFWCF (target 0) | Pending
TRICF (target 2.35 – 3) | Pending
TVCR (Target 0.79 – 2) | Pending
FAC (reporting) | Pending
TRICF · cases and frequency × 10^6 /HHT
Chart: Cases
| August · 0 cases | September · 0 cases | October · pending
Cases (left axis) | 0 | 0
Frequency (right axis) | 0 | 0
Target (right axis) | 2.35 | 2.35 | 2.35
TVCR · cases and frequency × 10^6 /km travelled
Chart: Cases
| August · 0 cases | September · 0 cases | October · pending
Cases (left axis) | 0 | 0
Frequency (right axis) | 0 | 0
Target (right axis) | 0.79 | 0.79 | 0.79
0
0
0
0
0
462
DAFWCF: lost-time cases × 10^6/ HHT
TRICF: recordable cases (FAT + DAFWC + MTC + RWC) × 10^6 / HHT
TVCR: Total Number of Work-Related Vehicle Accidents per Million Kilometres Travelled (× 10^6 / km travelled)
3
Notes: HSE INDICATORS - TALKING POINTS (cut-off Oct 27, 2026; Oct figures pending data load)
DAFWCF - Lost-time case frequency. Lost-time cases (DAFWC) x 10^6 / man-hours worked (HHT). Target 0. Aug-Sep: 0.
TRICF - Total recordable case frequency. (FAT + DAFWC + MTC + RWC) x 10^6 / HHT. Target 2.35 (range 2.35-3.00). Aug-Sep: 0.00, within target.
TVCR - Total vehicle accident rate. Work-related vehicle accidents x 10^6 / km travelled. Target 0.79 (range 0.79-2.00). Aug-Sep: 0.00, within target.
FAC - First aid cases. Reported for visibility, no target. Aug-Sep: 0.
HHT - Man-hours worked (denominator of TRICF/DAFWCF). Km driven - denominator of TVCR. Total workers - headcount in the month.
How to read the charts: bars = number of cases (left axis); green line = frequency (right axis); red dashed line = target (right axis). Frequency below the dashed line means the indicator is within target.
Pyramid (cumulative since Aug-26): FAT / DAFWC (top), MTC / RWC, FAC, incidents, and safety observations at the base. A wide base with an empty top is the expected profile: many proactive observations, no injuries.
Pending for Oct-26: all values marked in red must be loaded in the Compressor Plant and Pipeline monthly workbooks before issuing.
ANTECEDENTES SIN FECHA (texto original trasladado por legibilidad):
Road Traffic Accident Drill conducted on National Route N3.
Work Programs implemented for the transportation of pipelines from the port to the construction site.
No atribuir estos hechos a octubre sin confirmación de fecha y alcance.
FORMATO: 3.00 se muestra como 3; 2.00 como 2; 0.00 como 0. 2.35 y 0.79 se conservan porque son valores fraccionarios, no ceros de formato. No cambian las metas ni los datos. Se mantiene pendiente aclarar los rangos 2.35–3 y 0.79–2 frente a las metas de línea 2.35 y 0.79. Los históricos agosto–septiembre no pasan a ser resultados de octubre. Guion: DAFWCF = casos con días perdidos × 10^6/HHT; TRICF = casos registrables × 10^6/HHT; TVCR = accidentes vehiculares laborales × 10^6/km. FAC es conteo de primeros auxilios. Consolidar sumando numeradores y exposición; no promediar tasas.
ACLARACIÓN VIGENTE: estadísticas al 30/09; novedades de octubre en láminas separadas. No se exige cargar nuevas cifras de octubre para esta etapa. Se conserva 2.87% de capacitación. Los campos de octubre vacíos de la estructura no son cero ni permiten inferir ausencia de incidentes.

## Slide 4
1.1 > DEDICATED GAS PIPELINE UPDATE > HSE Indicators
CONFIDENTIAL
MANAGEMENT SAFETY WALKS
Chart: 
| Aug · total 2 | Sep · total 7 | Oct · pending
Monthly total | 2 | 7
Cumulative total | 2 | 9
SAFETY CAMPAIGNS
Chart: 
| Aug · total 2 | Sep · total 4 | Oct · pending
Monthly total | 2 | 4
Cumulative total | 2 | 6
DRILLS · target 100%
Chart: 
| Aug · total 2 | Sep · total 2 | Oct · pending
Monthly total | 2 | 2
Cumulative total | 2 | 4
OBSERVATIONS (OCS)
Chart: 
| Aug · total 167 | Sep · total 295 | Oct · pending
Monthly total | 167 | 295
Cumulative total | 167 | 462
TRAINING HOURS (HHS)
Chart: 
| Aug · total 1,853 | Sep · total 1,796 | Oct · pending
Monthly total | 1853 | 1796
Cumulative total | 1853 | 3649
TRAINING · REPORTED VALUE
Training % vs HHT
2.87%
HHS / HHT · CP + Pipeline · target ≥ 1%
WORKING DRAFT · 27 OCT 2026
4
Notes: PROACTIVE ACTIONS - TALKING POINTS
Management safety walks, safety campaigns and drills: bars = monthly total, line = cumulative since Aug-26. Drills target: 100% of those programmed.
Observations (OCS): safe-behaviour observations recorded in the month. Training hours (HHS): safety training man-hours; the Training % vs HHT card shows HHS / HHT, target >= 1.00%.
October bars remain pending. The training card displays 2.87%, as explicitly supplied by the user in the reference screenshot.
La nueva lámina de seguridad con espacios para fotos y novedades de octubre va inmediatamente después de esta lámina de barras. Los gráficos y sus valores no se actualizan. Simulacros: meta 100% de los programados exigibles al corte; el conteo por sí solo no demuestra cumplimiento. Capacitación: (HHS/HHT) ×100, meta de la fuente ≥1%. No se requiere carga de datos en esta fase temática.
ACTUALIZACIÓN DEL USUARIO: conservar 2.87% en Training % vs HHT, según el segundo pantallazo. Valor transcrito de la referencia recibida; no recalculado con HHS/HHT. Meta visible conservada: ≥1%. Los demás gráficos y pendientes se mantienen.
ACLARACIÓN VIGENTE: estadísticas al 30/09; novedades de octubre en láminas separadas. No se exige cargar nuevas cifras de octubre para esta etapa. Se conserva 2.87% de capacitación. Los campos de octubre vacíos de la estructura no son cero ni permiten inferir ausencia de incidentes.

## Slide 5
1.1 > DEDICATED GAS PIPELINE UPDATE > Safety | October Highlights
CONFIDENTIAL
OCTOBER 2026 · PHOTOS & RELEVANT HIGHLIGHTS · cut-off 27 Oct
OCTOBER PHOTO 1
Pending actual photo
Date / location / activity: pending confirmation
OCTOBER PHOTO 2
Pending actual photo
Date / location / activity: pending confirmation
SAFETY — RELEVANT OCTOBER TOPICS
[Safety highlights and photos pending]
Confirmed development · relevance · next step
WORKING DRAFT · 27 OCT 2026
5
Notes: NUEVA LÁMINA solicitada por el usuario a partir del comentario del jefe. Es una plantilla: no hay fotos reales ni novedades nuevas recibidas. Sustituir los recuadros por fotografías auténticas de octubre y completar fecha, lugar y actividad. No generar imágenes que aparenten evidencia de obra. Las novedades están pendientes de Leandro Doglio. La aclaración vigente es temas relevantes y datos iguales, sin exigir actualización de cifras. Describir hecho confirmado, relevancia y próximo paso. En seguridad, RN3 y programas de transporte pueden servir como antecedentes solo si se confirma su fecha; en ambiente no se informaron actividades específicas. No convertir sugerencias en hechos ejecutados.

## Slide 6
CONFIDENTIAL
3.0 > HELICOPTER SERVICE > Proposal
  Background:
    Vaca Muerta upstream major companies (including PAE, YPF & Pampa) have a contract with MODENA for the provision of its services which consists of having a helicopter available for use in the event of a medical emergency.
    Vista holds and manages a contract with MODENA covering aeromedical evacuation services for operators in Neuquén.
    VMOS has a contract in force with MODENA for such services. The service originated as an ad hoc decision by YPF following an Emergency Response Risk Analysis.
  Geographic Dispersion
    SMP pipeline route extends over 473 km along 2 provinces with sections located far away from high-complexity medical centres  Ground transportation may compromise the critical response time window during an emergency.
  Labour Context
    Impact of the VMOS precedent in the event of an accident requiring this service
    UOCRA agreement does not “explicitly” require this service for VMOS or SMP.
  Actual Use, No Saturation
    Existing regional contracts (Neuquén and VMOS) recorded 40 to 50 emergencies over 3 years (approximately 1 to 2 per month), indicating there is operational capacity to include the SMP route.
  Proposal to be discussed with Shareholders:
    Given the project’s extensive geographical footprint which includes remote areas with limited or no access to adequate medical infrastructure, it is recommended to have a helicopter available for emergency medical evacuation, particularly for incidents requiring medium- or high-complexity medical care.
WORKING DRAFT · 27 OCT 2026
6
Notes: Las afirmaciones sobre contratos regionales y contexto laboral son antecedentes de la fuente, no verificaciones nuevas. MODENA está citada como prestador, no como auditora. La utilización histórica no acredita por sí sola capacidad o disponibilidad de respuesta. Validar la información aplicable antes de emitir, sin inventar avances.

## Slide 7
Progress to date (cut-off Oct 27)
[Pending · YPF to provide status, milestones reached and dates]
Company auditing the service
[Pending · YPF to name the company that audits the service]
Option to add SESA
[Pending · YPF to confirm whether SESA can be added to the service]
CONFIDENTIAL
3.0 > HELICOPTER SERVICE > Progress update
WORKING DRAFT · 27 OCT 2026
7